## Release
Document Version | 1 | initial release | 2023-04-01
| 1.1 | removed macros | 2026-06-02
| 1.2 | Added risk dropdowns | 2026-06-02

## Project Info
Project Schedule provided by Net Zero Go. The intital tasks are aligned with the Net Zero Go plan of work
http://www.netzerogo.org.uk
Project Info
Edit yellow fields
Project title | My Super Project
Primary contact | Steve Buscemi
Lead organisation | Blandford
Project sponsor | My Sponsor name
PM name | My PM Name
How to use this document
1. Fill out project details
2. Review the stage activites and stages below.
3. Fill out personal and responibilities
4. Review and update schedule if required
5. Fill out Risk log
6. Fill out stakeholder mapping
Net Zero Go project activites and stages
Edit these to change lookup lists in Risks
Stage 0: Strategic Definition | Stage 1: Preparation and Briefing | Stage 2: Concept Design | Stage 3: Spatial Coordination and Localisation | Stage 4: Technical Design | Stage 5: Construction, Integration and Installation | Stage 6: Handover | Stage 7: Use (and Operation)
Project Cost | Project Budget, Costs, and Revenues | Concept Design | Planning Application | Detailed Technical Design | Commissioning | Project Performance Review | Customer Management
Strategic Capability Identification | Feasibility Studies | Project Programme Development | Locally Coordinated Design | Building Regulations Application | Practical Completion | Plan for Use Strategy | Verify project outcomes
Project Risks, Opportunities, Constraints and Dependencies | Site Information and Surveys | Cost Plan | System Connection Applications | Construction Information | Quality Monitoring | Aftercare Tasks | Facilities management
Site Appraisals | Capability Identification |  | Consultation and Community Engagement | Confirm Network Connections | Site Logistics | Post-Handover Evaluation | Asset management
Define Requirements and outcomes | Procurement Strategy |  |  | Spatially Coordinated Design | Operations Manual | Handover | Post Commission evaluation
Review Feedback from previous projects | Project Programme |  |  |  | Construction Programme
Funding and Investment Options

## Skills (hidden)
Project Cost
Strategic Capability Identification
Project Risks, Opportunities, Constraints and Dependencies
Site Appraisals
Define Requirements and outcomes
Review Feedback from previous projects
Project Budget, Costs, and Revenues
Feasibility Studies
Site Information and Surveys
Capability Identification
Procurement Strategy
Project Programme
Funding and Investment Options
Concept Design
Project Programme Development
Cost Plan
Planning Application
Locally Coordinated Design
System Connection Applications
Consultation and Community Engagement
Detailed Technical Design
Building Regulations Application
Construction Information
Confirm Network Connections
Spatially Coordinated Design
Commissioning
Practical Completion
Quality Monitoring
Site Logistics
Operations Manual
Construction Programme
Project Performance Review
Plan for Use Strategy
Aftercare Tasks
Post-Handover Evaluation
Handover
Customer Management
Verify project outcomes
Facilities management
Asset management
Post Commission evaluation

## Responsibilities
Project Gant Chart provided by Net Zero Go. The intital tasks are aligned with the Net Zero Go plan of work
http://www.netzerogo.org.uk
RACIS Matrix - Enter your team and allocate responsibilities using the dropdowns in the matrix below
My Super Project | [15 empty] | Roles and Responsibilities
R | Responsible | Assigned to complete the task or deliverable.
A | Accountable | Accountable for delivery. Authority to progress project through goverance stages
C | Consulted | An adviser, stakeholder, or subject matter expert who is consulted before a decision or action.
I | Informed | Must be informed after a decision or action.
S | Support | Provides support during implementation.
|  |  |  | Stage | Task | Task | Task | Task | Task | Task | Stage | Task | Task | Task | Task | Task | Task | Task | Stage | Task | Task | Task | Stage | Task | Task | Task | Task | Stage | Task | Task | Task | Task | Task | Stage | Task | Task | Task | Task | Task | Task | Stage | Task | Task | Task | Task | Task | Stage | Task | Task | Task | Task | Task
|  |  |  | Stage 0: Strategic Definition | Project Cost | Strategic Capability Identification | Project Risks, Opportunities, Constraints and Dependencies | Site Appraisals | Define Requirements and outcomes | Review Feedback from previous projects | Stage 1: Preparation and Briefing | Project Budget, Costs, and Revenues | Feasibility Studies | Site Information and Surveys | Capability Identification | Procurement Strategy | Project Programme | Funding and Investment Options | Stage 2: Concept Design | Concept Design | Project Programme Development | Cost Plan | Stage 3: Spatial Coordination and Localisation | Planning Application | Locally Coordinated Design | System Connection Applications | Consultation and Community Engagement | Stage 4: Technical Design | Detailed Technical Design | Building Regulations Application | Construction Information | Confirm Network Connections | Spatially Coordinated Design | Stage 5: Construction, Integration and Installation | Commissioning | Practical Completion | Quality Monitoring | Site Logistics | Operations Manual | Construction Programme | Stage 6: Handover | Project Performance Review | Plan for Use Strategy | Aftercare Tasks | Post-Handover Evaluation | Handover | Stage 7: Use (and Operation) | Customer Management | Verify project outcomes | Facilities management | Asset management | Post Commission evaluation
| Team | Role | Name
| Leadership | Project sponsor | My Sponsor name | I | R
| Project | PM name | My PM Name |  | A |  | R
| Consultant | Lead Technical Consultant | Mrs Consultant
| Project | Project officer | Miss Project Officer | [7 empty] | R

## ProjectSchedule
Project Schedule provided by Net Zero Go. The intital tasks are aligned with the Net Zero Go plan of work
http://www.netzerogo.org.uk
Project Schedule - update as required
My Super Project
| Update progress, dates and assignees |  | Project Start: | 2022-09-27
|  |  | Today: | 2026-06-02
|  |  | Display Week: | 1 | 2022-10-04 |  |  |  | 2022-09-26 | [6 empty] | 2022-10-03 | [6 empty] | 2022-10-10 | [6 empty] | 2022-10-17 | [6 empty] | 2022-10-24 | [6 empty] | 2022-10-31 | [6 empty] | 2022-11-07 | [6 empty] | 2022-11-14 | [6 empty] | 2022-11-21 | [6 empty] | 2022-11-28 | [6 empty] | 2022-12-05 | [6 empty] | 2022-12-12 | [6 empty] | 2022-12-19 | [6 empty] | 2022-12-26 | [6 empty] | 2023-01-02 | [6 empty] | 2023-01-09 | [6 empty] | 2023-01-16 | [6 empty] | 2023-01-23 | [6 empty] | 2023-01-30 | [6 empty] | 2023-02-06 | [6 empty] | 2023-02-13 | [6 empty] | 2023-02-20 | [6 empty] | 2023-02-27 | [6 empty] | 2023-03-06 | [6 empty] | 2023-03-13 | [6 empty] | 2023-03-20
 | time axis 2022-09-26 to 2023-03-26
Type | Item | ASSIGNED TO | PROGRESS | START | END | Position | Weeks | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Stage | Stage 0: Strategic Definition |  | 44.17% | 2022-10-01 | 2022-11-07 | 27.6204 | 5.4286 | 38
Task | Project Cost |  | 100% | 2022-10-01 | 2022-11-01 | 27.5138 | 4.5714 | 32
Task | Strategic Capability Identification |  | 20% | 2022-10-01 | 2022-11-03 | 58.366 | 4.8571 | 34
Task | Project Risks, Opportunities, Constraints and Dependencies |  | 30% | 2022-10-01 | 2022-11-04 | 12.7958 | 5 | 35
Task | Site Appraisals |  | 40% | 2022-10-01 | 2022-11-05 | 33.3835 | 5.1429 | 36
Task | Define Requirements and outcomes |  | 50% | 2022-10-01 | 2022-11-06 | 30.7325 | 5.2857 | 37
Task | Review Feedback from previous projects |  | 25% | 2022-10-01 | 2022-11-07 | 86.1743 | 5.4286 | 38
Stage | Stage 1: Preparation and Briefing |  | 20% | 2022-10-01 | 2023-01-20 | 10.909 | 16 | 112
Task | Project Budget, Costs, and Revenues |  | 0% | 2022-11-10 | 2023-01-15 | 25.443 | 9.5714 | 67
Task | Feasibility Studies |  | 10% | 2022-10-01 | 2022-11-02 | 60.8281 | 4.7143 | 33
Task | Site Information and Surveys |  | 10% | 2022-11-11 | 2023-01-16 | 52.246 | 9.5714 | 67
Task | Capability Identification |  | 50% | 2022-11-12 | 2023-01-17 | 76.1611 | 9.5714 | 67
Task | Procurement Strategy |  | 70% | 2022-11-13 | 2023-01-18 | 17.5252 | 9.5714 | 67
Task | Project Programme |  | 0% | 2022-11-14 | 2023-01-19 | 23.1207 | 9.5714 | 67
Task | Funding and Investment Options |  | 0% | 2022-11-15 | 2023-01-20 | 15.1668 | 9.5714 | 67
Stage | Stage 2: Concept Design |  | 0% | 2023-01-20 | 2023-02-02 | 75.6455 | 2 | 14
Task | Concept Design |  | 0% | 2023-01-20 | 2023-02-02 | 84.7076 | 2 | 14
Task | Project Programme Development |  | 0% |  |  | 63.5464
Task | Cost Plan |  | 0% |  |  | 95.8912
Stage | Stage 3: Spatial Coordination and Localisation |  | 0% | 2023-02-02 | 2023-03-10 | 39.5426 | 5.2857 | 37
Task | Planning Application |  | 0% | 2023-02-02 | 2023-02-02 | 94.9727 | 0.14286 | 1
Task | Locally Coordinated Design |  | 0% |  |  | 85.8683
Task | System Connection Applications |  | 0% |  |  | 60.87
Task | Consultation and Community Engagement |  | 0% | 2023-02-02 | 2023-03-10 | 56.6849 | 5.2857 | 37
Stage | Stage 4: Technical Design |  | 0% | 2023-03-10 | 2023-04-30 | 99.6307 | 7.4286 | 52
Task | Detailed Technical Design |  | 0% | 2023-03-20 | 2023-04-30 | 81.741 | 6 | 42
Task | Building Regulations Application |  | 0% |  |  | 30.4851
Task | Construction Information |  | 0% |  |  | 41.3897
Task | Confirm Network Connections |  | 0% |  |  | 58.0501
Task | Spatially Coordinated Design |  | 0% |  |  | 70.2797
Stage | Stage 5: Construction, Integration and Installation |  | 0% | 2023-04-30 | 2023-05-30 | 68.9726 | 4.4286 | 31
Task | Commissioning |  | 0% | 2023-04-30 | 2023-05-30 | 23.5405 | 4.4286 | 31
Task | Practical Completion |  | 0% |  |  | 48.7598
Task | Quality Monitoring |  | 0% |  |  | 32.9231
Task | Site Logistics |  | 0% |  |  | 24.9673
Task | Operations Manual |  | 0% |  |  | 70.9919
Task | Construction Programme |  | 0% |  |  | 65.1348
Stage | Stage 6: Handover |  | 0% | 2023-05-30 | 2023-06-02 | 81.956 | 0.57143 | 4
Task | Project Performance Review |  | 0% | 2023-05-30 | 2023-06-02 | 53.0574 | 0.57143 | 4
Task | Plan for Use Strategy |  | 0% |  |  | 51.148
Task | Aftercare Tasks |  | 0% |  |  | 77.3576
Task | Post-Handover Evaluation |  | 0% |  |  | 77.6513
Task | Handover |  | 0% |  |  | 37.5465
Stage | Stage 7: Use (and Operation) |  | 0% | 2023-06-02 | 2023-07-02 | 28.2166 | 4.4286 | 31
Task | Customer Management |  | 0% | 2023-06-02 | 2023-07-02 | 11.0994 | 4.4286 | 31
Task | Verify project outcomes |  | 0% |  |  | 93.2351
Task | Facilities management |  | 0% |  |  | 90.2889
Task | Asset management |  | 0% |  |  | 46.6925
Task | Post Commission evaluation |  | 0% |  |  | 28.0098
2018-01-13
Note on I10: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## Milestone Chart
Project Gant chart provided by Net Zero Go.
http://www.netzerogo.org.uk
Project Milestone Chart
This provides a simple milestone chart for your project. This runs off data in the project schedule tab
Type | Stage
END | Item | Position
2022-11-07 | Stage 0: Strategic Definition | 51.7885
2023-01-20 | Stage 1: Preparation and Briefing | 28.2433
2023-02-02 | Stage 2: Concept Design | 19.2117
2023-03-10 | Stage 3: Spatial Coordination and Localisation | 74.6509
2023-04-30 | Stage 4: Technical Design | 34.6259
2023-05-30 | Stage 5: Construction, Integration and Installation | 43.956
2023-06-02 | Stage 6: Handover | 20.1399
2023-07-02 | Stage 7: Use (and Operation) | 80.8859

## Risks
RAID Log provided by Net Zero Go. The categories are aligned with Net Zero Go Risk Categories
http://www.netzerogo.org.uk
Risk and mitigation Log
My Super Project | [14 empty] | Roles and Responsibilities
Project Sponsor |  | My Sponsor name
PM |  | My PM Name
Score before mitigation |  | 6
Score after mitigation |  | 2
Cost of mitigation |  | 999
Risk | Date raised | Status | Raised By | Owner | Risk description | Risk Category | Stage project affected | Activity Affected | Effect of Impact on cost, quality and timetable | Probability | Impact | Risk Score | Mitigation | Mitigation Cost | Actions required | Probability after mitigation | Impact after mitigation | Risk Score after mitigation
Risk 1 | 2022-01-01 | Open | concerned citizen | My PM Name | Description | Economic | Stage 0: Strategic Definition | Project Cost | No effect | 2 | 3 | 6 | Mitigation | 999 | Actions to achieve mitigation | 2 | 1 | 2
[12 empty] | 0 | [5 empty] | 0
Note on E12: Select from your names list in the RACI sheet
Note on H12: Select from project stages on project info sheet
Note on I12: Select from project activities on project info

## Tables (hidden)
Risk categories
Risk Categories | Description
Technical | What the local energy project needs to do, what it is and how it performs in its environment and with related systems.
Market | Commercial arrangements for the local energy project that result in value being realised.
Social | People or groups involved in or impacted by a local energy project and its stakeholders, environment and related systems.
Policy | Government interventions to support or constrain a local energy project and its stakeholders, environment and related systems.
Legal | Law relating to a local energy project and its stakeholders, environment and related systems, including regulation.
Economic | Economic impact or constraints on a local energy project and its stakeholders, environment and related systems.
Environment | External effects associated with the development, production, utilisation, support and retirement of a local energy project and its stakeholders, environment and related systems.
Organisation | Organisation(s) delivering the project, including the supply chain.
Project | Delivery of local energy projects.
Schedule | Relating to timing or delay of the delivery of a local energy project due to internal and external factors.
Risk Status
Open
Assessed
Controlled
Triggered
Closed

## Stakeholder Analysis
RAID Log provided by Net Zero Go. The categories are aligned with Net Zero Go Risk Categories
http://www.netzerogo.org.uk
Stakeholder log
My Super Project | [12 empty] | Roles and Responsibilities
Commitment
P - passive, -1 against, 0 neutral,1 supportive
Stakeholder name | Title | Email | Influence | Interest | Priority | SME? | Decision-Maker | Comm. Freq. | Comm. Method | Current Level | Required Level | Notes
Ed Harris | Finance | ed@email | 3 | 3 | 9 | Yes | No | Monthly | Email | P | -1
sadfsdf |  |  | 3 | 3 | 9 | No |  |  |  | -1 | 1
fsdf | sdf |  | 2 | 3 | 6 |  |  |  |  | 0 | 1
sdfs |  |  | 2 | 3 | 6 |  |  |  |  | 1 | 1
sdfs |  |  | 2 | 2 | 4 |  |  |  |  | -1 | 1
dfsd | df |  | 1 | 3 | 3 |  |  |  |  | 1 | 1
Don Lu | Engineer | donlu@email | 1 | 2 | 2 | Yes | Yes | Weekly | In Person | -1 | 1
Jo Ann | Design | jo@email | 2 | 1 | 2 | No | No | Weekly | Phone | 1 | 1
sdafs |  |  | 1 | 1 | 1 |  |  |  |  | -1 | 1
new name |  |  | 1 | 1 | 1 |  |  |  |  | 1 | 1