## Sheet1
Topic | Decision to make | Options | Considerations
Business Targeting | Should businesses be included/targeted only if they own the freehold of their premise? | Yes - freeholders only Targeting - freeholders targeted, but leasholders included if clear engagement from landlord No - landlord engagement a key consideration but targeting is wide | Limiting to freeholders may significantly limit the pool of business that can take part. Limiting to freeholders may target businesses who could take forward solar without this support. Accepting leaseholders adds complexity to the legal agreements and likely causes delays. Accepting leaseholders adds risk from business leaving building.
Business Targeting | If leaseholders are included, should the PPA be issued separately or be passported through the landlord? | Separate - issue the PPA to the leaseholder Passported - ask the landlord to create an identical PPA to passport the energy on to the leaseholder | Seperating the PPA adds risks of the contracts being less firmly tied, so issues with one contract may not necessarily allow for changes in the other. Passporting the PPA requires the freeholder's legal team to review and manage the contract outside of the project owner's activities.
Business Targeting | Should the scheme target particular sectors of business or roof sizes? | Heavy targeting - the scheme is designed for and open to a specific sector or geography to align with political priorities; with specific references in communications and specific direction to business advisors to showcase to the target groups Light targeting - the scheme is designed and open to all sectors and geographies, but communication activities and business referals are targeted to specific sectors or geographies No targeting - the scheme is designed and open to all sectors and geographies with general communications and wide referals | Targeting allows for the project to align more closely with political and economic priorities, e.g. alignement with the IS-8. Targeting may reduce the communications costs/capacity requirement by having fewer activities required. Targeting may make it easier for business advisors to understand and showcase the project. Targeting may make it easier to design and procure the solar systems as each will be relatively similar. Targeting may impact the financial impacts of the project, with smaller sites resulting in typically lower IRRs and larger sites typically higher IRRs. Targeting may result in some businesses and sectors feeling overlooked and create inequalities. Targeting will reduce the pool of potential businesses who may sign-up to the scheme.
Contract Terms | How long should the lease and PPA term be set for? | 25 years 30 years 35 years | The contract length should be set according to the expected lifetime of the solar system. A longer contract length (presuming no system replacement) extends the amount of LA financial return and business benefit. A shorter contract length reduces the risk of the contract extending beyond the lifetime of the panels.
Contract Terms | How should the system ownership/removal be dealt with at the end of the contract? | Gifted to landlord Sold to landlord Removed at LA's cost | Gifting the system at the end of the contract provides a simple end of contract process. Gifting the system may require subsidy control assessments. Selling to the landlord allows for the LA to secure small additional funds if the landlord agrees to buy the system. Removal of the system will require decommissioning costs.
Contract Terms | Should the building owner be entitled to free removal of the system for the purposes of roof repair? | Multiple times Once No | Allowing for free removal will provide piece of mind and avoid disincentive to the landlord. Allowing free removal will incur cost and opportunity cost to the project. Financial assessments should consider how many times it is reasonable to offer this removal to ensure financial viability is not negatvely impacted.
Contract Terms | Should the contract include provision for the LA to compensate the landlord for any increase in insurance premiums? | Yes No | Compensating will incur a small additional cost for the LA, which could be credited on the first bill each year. Compensating will provide piece of mind and avoid disincentive to the landlord
Contract Terms | Should the contract include a minimum spend condition? | Yes - set higher Yes - set lower No | Setting a minimum spend helps ensure financial viability for the LA. The higher the minimum spend, the greater the protection for the LA and the lower potential benefit for the business. The minimum spend level should be set following analysis of expected on-site usage during the design phase.
Outsourcing | Will initial feasibility work and system designs be developed internally or outsourced? | Internally Service Agreement with partner Outsourced | Where internal expertise exists within the organisation or its partner, it would be quicker and cheaper to design the systems internally. Full engineering expertise may not be neeeded; high level sizing may be sufficient with full detailed design being procured as a design and delivery contract. If no internal expertise is available, system design must be outsourced.
Outsourcing | Will ongoing system performance review be reviewed internally or outsourced? | Internally Service Agreement with partner Outsourced | Where internal expertise exists within the organisation or its partner, it would be quicker and cheaper to manage the systems internally. If no internal expertise is available, management must be outsourced.
Outsourcing | Will communications and sign-ups be delivered internally or outsourced? | Internally Service Agreement with partner Outsourced | Where internal capacity and contacts exist within the organisation or its partner, it would be quicker and cheaper to manage the systems internally. If no internal capacity and contacts are available, communications must be outsourced.
Outsourcing | Will due dilligence on businesses be delivered internally or outsourced? | Internally Service Agreement with partner Outsourced | Where internal capacity and expertise exist within the organisation or its partner, it would be quicker and cheaper to udertake due dilligence internally. If no internal capacity and expertise are available, due dilligence must be outsourced. Project Board decision making is expected to be required for the level of due dilligence required. Take advice from previous grant and loan schemes.
Outsourcing | Will capital delivery project management be delivered internally or outsourced? | Internally Service Agreement with partner Outsourced | Where internal expertise exists within the organisation or its partner, it would be quicker and cheaper to project manage internally. If no internal expertise is available, project management must be outsourced.
Outsourcing | Will planning permission applications be managed internally or outsourced? | Internally Service Agreement with partner Outsourced | Where internal expertise exists within the organisation or its partner, it would be quicker and cheaper to submit planning applications internally. If no internal expertise is available, planning applications design must be outsourced.
Outsourcing | Will grid connection applications be managed internally or outsourced? | Internally Service Agreement with partner Outsourced | Where internal expertise exists within the organisation or its partner, it would be quicker and cheaper to submit DNO applications internally. If no internal expertise is available, DNO applications design must be outsourced.
Outsourcing | If multiple elements are to be outsourced, should the outsourcing be bunlded into one procurrment or in separate procurements? | Separate Part-bundled Bundled | Separated procurements can be timed for exact need. Separated procurements can allow for more detailed KPIs and monitoring/control. Separated procurements can enable more specialised companies to enact each element. Bundled procurements can save time in the procurement process. Bundled procurements minimise the contract management requirements. Bundled procurements can enable financial efficiencies.
Outsourcing | If outsourcing management aspects, should the contract be a fixed-fee or a concession/revenue split model? | Fixed fee Revenue split | Fixed fee management contracts ensure that the LA has stable costs for financial planning. Revenue split contracts may incentivise the delivery partner to maxmise system efficiency.
Outsourcing | When procuring the capital delivery partner, will procurement be on a site-by-site basis, or bundled? | Separate Part-bundled Bundled | Separated procurements can be timed for exact need. Separated procurements can allow for more detailed KPIs and monitoring/control. Bundled procurements can save time in the procurement process. Bundled procurements minimise the contract management requirements. Bundled procurements can enable financial efficiencies.
PPA rate | Should the PPA rate be set as a fixed rate with inflation or as a discounted rate? | Fixed with inflation - the PPA rate and inflation rate are set at a rate determined by the LA for the duration of the contract Discounted - the PPA rate is set at a % discount below 'background' electricity bills | Fixed rate PPA provides long-term assurance to both the LA and business of what the project revenues/costs are set to be, allowing more accurate long-term forecasting. Fixed rate PPA allows the LA to set a rate that guarentees long-term financial viability of the project. Discounted PPA ensures that the business benefits from the project across its lifetime. Discounted PPA increases the administrative and management burden by having quarterly reviews of the PPA rate.
PPA rate | If PPA rate is fixed, what should the initial fixed rate be? | 15-20p/kWh | The higher the PPA rate is set, the better the financial return for the LA. The lower the PPA rate is set, the better the financial benefit for the business.
PPA rate | If PPA rate is discounted, what should the discount percent be? | 10-50% | The lower the discount rate set, the better the financial return for the LA. The higher the discount rate is set, the better the financial benefit for the business.
PPA rate | If PPA rate is discounted, what should be the benchmark used for discounting? | Business electricity bill National average electricity bill dataset | Business electricity bill benchmarking ensures that the business benefits from the project by the exact discount rate, rather than a different % due to a different bill cost to the national average. Business electricity bill benchmarking requires open and honest provision of the quarterly electricity bills by the business, which they may not be able to or wish to provide. National average benchamrking ensures that the PPA rate is set evenly for all businesses involved in the project. National average benchmarking risks the dataset not being available and a new benchmark having to be found.
PPA rate | If PPA rate is discounted, where should the floor price be set? | 12-15p/kWh | The floor rate should be set at the lowest rate that allows for the project to be financially viable for the LA according to the targets of the priority metrics set. The higher the floor price rate is set, the better the financial return for the LA. The lower the floor price is set, the better the financial benefit for the business.
PPA rate | For either PPA rate, should a cap price be included and where should it be set? | Yes - 25-40p/kWh No | Setting a cap price protects the businesses from extreme price hikes. Setting a cap price restricts the financial benefit available to the LA. The cap price should be set with consideration of the maximum financial benefit level the LA desires. The cap price should be set with consideration of expected inflationary impacts on the project costs. The higher the cap price rate is set, the better the financial return for the LA. The lower the cap price is set, the better the financial benefit for the business.
Site Acceptance | What project outputs should be prioritised in designing and accepting a site? | IRR ROI Payback period NPV tCO2e Business savings Legal complexity Planning permission Strategic alignment | The project should both consider each individual project's outputs and the whole programme's outputs; the programme may allow for lower outputs for some sites to be subsidised by another if there are particular political or social reasons. Prioritising annual percentage returns best showcasing the relative success of the project in comparison to other projects and options. Prioritising payback period provides greater security for LA budgets. Prioritising NPV allows for best maxmisation of the finanical benefits from the project. Prioritising tCO2e maximises the environmental benefits of the project. Prioritising business savings maximises business benefit, while posing financial risks for the LA. Prioritising legal complexity or planning permission allows for the project to progress more smoothly to delivery.